## excel
/Proyecto/PSP Fundamentals & Advanced/Program 6
PSP2.1 Project Plan Summary
Project Settings
Project Owner | Daniel Melgarejo
Start Date
Completion Date | abr 19, 2017 10:50:45 PM |  |  |  | Completed: *
Keywords
Language
Overall Metrics
Summary | Plan | Actual | A la Fecha
Size/Hour | 31.3 | 16.3 | 28.1
Planned Time | 0.095833 |  | 0.75764
Actual Tiempo |  | 0.13056 | 0.99583
CPI (Cost-Performance Index) |  |  | 0.76
% Reuse | 0% | 0% | 16.4%
% New Reusable | 0% | 0% | 51.8%
Test Defects/KLOC or equivalent | 3.22 | 0 | 2.98
Total Defects/KLOC or equivalent | 19.3 | 39.2 | 20.8
Yield % | 83.3% | 100% | 92.3%
Code Review Rate | 831 | 204 | 650
% Appraisal COQ | 7.54% | 12.2% | 8.16%
% Failure COQ | 26.9% | 17% | 25.6%
COQ A/F Ratio | 0.28 | 0.72 | 0.32
PQI | 0.05 | 0.03 | 0.05
Program Size
| Plan | Actual | A la Fecha
Base (B) | 281 | 272 | 317
Deleted (D) | 0 | 0 | 20
Modified (M) | 0 | 0 | 28
Added (A) | 72.2 | 51 | 898
Reused (R) | 0 | 0 | 235
Added and Modified (A+M) | 72.2 | 51 | 672
Total Size (T) | 353 | 323 | 1430
Total New Reusable | 0 | 0 | 348
Estimated Proxy Size (E) | 118 | 80 | 1261
Upper Prediction Interval (70%) | N/A
Lower Prediction Interval (70%) | N/A
Time In Phase
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0.013889 | 0.0097222 | 0.13264 | 13.3%
DiseÃ±o | 0.0097222 | 0.0076389 | 0.093056 | 9.34%
RevisiÃ³n de DiseÃ±o | 0.0034722 | 0.0055556 | 0.038194 | 3.84%
CodificaciÃ³n | 0.032639 | 0.069444 | 0.3625 | 36.4%
RevisiÃ³n de CodificaciÃ³n | 0.0034722 | 0.010417 | 0.043056 | 4.32%
CompilaciÃ³n | 0.00625 | 0.010417 | 0.067361 | 6.76%
Pruebas | 0.019444 | 0.011806 | 0.1875 | 18.8%
Postmortem | 0.0076389 | 0.0055556 | 0.071528 | 7.18%
Total | 0.095833 | 0.13056 | 0.99583
Total Time UPI (70%) | N/A
Total Time LPI (70%) | N/A
Defects Injected
| Plan | Actual | A la Fecha | % A la Fecha
Antes de Desarrollo | 0 | 1 | 1 | 7.69%
PlaneaciÃ³n | 0.35 | 0 | 3 | 23.1%
DiseÃ±o | 0.35 | 1 | 4 | 30.8%
RevisiÃ³n de DiseÃ±o | 0 | 0 | 0 | 0%
CodificaciÃ³n | 0.7 | 0 | 6 | 46.2%
RevisiÃ³n de CodificaciÃ³n | 0 | 0 | 0 | 0%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0 | 0 | 0 | 0%
Total | 1.4 | 1 | 13
Defects Removed
| Plan | Actual | A la Fecha | % A la Fecha
PlaneaciÃ³n | 0 | 0 | 0 | 0%
DiseÃ±o | 0.12 | 0 | 1 | 7.14%
RevisiÃ³n de DiseÃ±o | 0.23 | 1 | 3 | 21.4%
CodificaciÃ³n | 0.7 | 1 | 7 | 50%
RevisiÃ³n de CodificaciÃ³n | 0.12 | 0 | 1 | 7.14%
CompilaciÃ³n | 0 | 0 | 0 | 0%
Pruebas | 0.23 | 0 | 2 | 14.3%
Total | 1.4 | 2 | 14
After Development | 0.58 | 0 | 5
Defect Removal Efficiency
| Plan | Actual | A la Fecha
Defects/Hour - Design Review | 2.68 | 7.5 | 3.27
Defects/Hour - Code Review | 1.34 | 0 | 0.97
Defects/Hour - Compile | 0 | 0 | 0
Defects/Hour - Test | 0.5 | 0 | 0.44
DRL (DLDR/UT) | 5.38 | 16.9 | 7.36
DRL (Code Review/UT) | 2.69 | 0 | 2.18
DRL (Compile/UT) | 0 | 0 | 0
Adapted from "PSP Materials," copyright © 2006 Carnegie Mellon University. Used by permission.
Reporte generado a las 11:07 PM el 19/04/2017